## Slide 1: Ad-Hoc Committee on Employment
Updates for July HIV planning group meeting

## Slide 2: Collaboration with Temple University to conduct employment needs assessment
Invited by Dr. Eva Weiss of Temple University to contribute to a Comprehensive Statewide Needs Assessment (CSNA).
  CSNA informs the PA Vocational Rehabilitation State Plan, and consequently budget, and identifies evidence-based practices and recommendations to better meet the employment/employment service needs of Pennsylvanians with disabilities.
  Ad-hoc committee role:
    Assist with developing brief online survey to identify employment needs of PLHIV
    Assist with the distribution of the survey link to key stakeholders
    Conduct 20 individual interviews to add qualitative data
    Identity other existing data sources that may help to inform employment needs
      Medical Monitoring Project

## Slide 3: Updates
  Finalized Draft of Employment Needs Survey
    Have been stalled due to technical difficulties Temple’s survey software
      Will then need to translate into Spanish, get IRB approval, and distribute widely throughout the state.
  Planning for qualitative data collection
    Decided to complete 20 individual interviews instead of focus groups.
      Given delays, Temple no longer able to fund the interviewer position so PSU graduate assistant with expertise in qualitative research will complete the interviews and share the data with Temple.
    Developing protocols
      Draft questions have been proposed for the Ad-hoc committee review.
      Selection for interviewees will be based on selecting a diverse range of individuals who complete the survey and volunteer to participate in paid research
        Each interviewee will be paid $50.00 for the interview through Temple’s budget
  Based upon finding provide input to the CSNA report that Temple staff will present to OVR
    Best Practices
      This will include recommendations for best practices.

## Slide 4: Meeting Schedule
Every other Tuesday from 11 to noon.
Next meeting is July 16th
If interested in joining the meetings, contact Paul Kabera
  PHK28@pitt.edu